## Revision History
Project | Open Cellular Connect -1
Board Name | Radio Frequency - Software Defined Radio
Build | Life - 3 (Rev C)
Changes Log | From RF_Life - 2 to RF_SDR_Life-3
Change History
Date | Version | Author | Remarks
30th NOV 2016 | Release Version for FE Life-3 | Srinivas S

## Change_log
FE Life-3 Design Change Log
S.No | Date | Reference Designator | Changes Done | Impact to BOM | Impact to Schematic | Impact to Layout | Impacted Design Revision | Fixed Design Revision | Fix Status | Reason for change
1 | 2016-11-30 | J3303 | Added 96 pin connector | YES | YES | YES | - | REVC | close | splited SDR and RF board
2 |  | U2230 | TX digital attenuator changed to 31dB | YES | YES | NO | REVB | REVC | close | TX attenation range control change from 15dB to 31 dB
3 |  | FL3312,FL3313 | HB_BPF added | Yes | YES | YES | REVB | REVC | close | HB_BPF added -TX spurious
4 |  | FL3310,FL3314 | LB BPF added | Yes | YES | YES | REVB | REVC | close | LB_BPF added-TX spurious
5 |  | U7146,U7147 | LB isolator added | Yes | YES | YES | REVB | REVC | close | LB isolator added reverse power isolation to PA
6 |  | U7148,U7149 | HB isolator added | Yes | YES | YES | REVB | REVC | close | HB isolator added reverse power isolation to PA
7 |  | U7156,U7155 | RX LNA added | Yes | YES | YES | REVB | REVC | close | Better noise figure
8 |  | U304 | EEPROM ADDED-CAT24C256WI-GT3 | Yes | YES | YES | - | REVC | close | To store configuration datai n FE board
9 |  | FL3316,ATT2602 | low power duplexer, fixed 10 dB attenuator added-SAYEY897MBC0B0A | Yes | YES | YES | - | REVC | close | For testing 2G loop back
10 |  | U7157 | IO expander added-PCA9557 | Yes | YES | YES | - | REVC | close | For stap pins
11 |  | U4D5,U4D3 | I2C buffers added-PCA9517 | Yes | YES | YES | - | REVC | close | For isolation TIVA I2C to FE I2C
12 |  | U717 | AND gate added-SN74LV08A | Yes | YES | YES | - | REVC | close | anding Separate reset for RF board
13 |  | U7159 | level transulator added-SN74AVC4T774RGYR | Yes | YES | YES | - | REVC | close | for isolating SDR and FE signals
14 |  | U7153 | level transulator added-SN74AVC1T45DRLR | Yes | YES | YES | - | REVC | close | Voltage conversion of 3p3V to 2p5V
15 |  | U71,U7,U8,U9,U10,J4,U11,U12,U13 | Added 2G module Power supply,buffers,LDO and SIM connector | Yes | YES | YES | - | REVC | close | 2G module-Moved from GBC to RF front end board
16 |  | U40,U41 | Temparatures sensor changed to -ADT7481 | Yes | YES | YES | REVB | REVC | close | used tdiodes and THERM alert for temparature measurement
17 |  | U7122,U7123,U7136,U7137,U7139,U7140,U7141,U7142,U7161,U7162 | Added RF test connectors | Yes | YES | YES | REVB | REVC | close | Added RF test connectors for testing
18 |  | U7132,U7133,U7134 | Added level transulators -74AVC8T245PW | Yes | YES | YES | - | REVC | close | For isolation FPGA to RF front end signals
19 |  | U7130,U2604,U2600,U2500,U2504,U2502,U2701,U7131,U3204,U3200,U3100,U3103,U3104,U3301 | Removed all Rf switches in the design | Yes | YES | YES | REVB | REVC | close | By default only one band comenents is mounted in the design.
20 |  | U3204,U7151 | Added SPDT switch | Yes | YES | YES | REVB | REVC | close | switching between RF chain and loop back testing
21 |  | U3700,U3701,U3900,U3901 | Removed LDOS from the design | Yes | YES | YES | REVB | REVC | close | To reduce the BOM cost and changed the power supply to PA's
22 |  | U303,U7126 | Removed MUX IC's | Yes | YES | YES | REVB | REVC | close | All switches removed by default only one band componentswill be assembled on the board
23 |  | J3305,J3308,J3306,J3307 | Removed jumpers | Yes | YES | YES | REVB | REVC | close | All switches removed in the design- no switch controls
24 |  | U2003,U1803 | Removed Temparature sensors | Yes | YES | YES | REVB | REVC | close | Temparature sensors changed to ADt7481
25 |  | FB3412,FB3413,FB3415,FB3414,FB3416,FB3417,FB3418,FB3419 | Replace 0R jumper R11090 for a ferrite bead like FB2401 Do the same thing to have a ferrite bead on every RF power destination. (Like on the right) | Yes | YES | YES | REVB | REVC | close | Replace 0R jumper R11090 for a ferrite bead like FB2401 Do the same thing to have a ferrite bead on every RF power destination. (Like on the right)
26 |  | JP3,D5,D10,R513,D10126 | 12V LED indication and 12v connectoradded to RF board, | Yes | YES | YES | REVB | REVC | close | 12V LED indication and 12v connectoradded to RF board,
27 |  | U2000,U4300,U4301 | IO expander and level translayot for switch controls were deleted | Yes | YES | YES | REVB | REVC | close | IO expander and level translayot for switch controls were deleted
28 |  | U2700,ATT2700,ATT2701,J2702 | Removed 20 dB coupler ,fixed attenuator and connector | Yes | YES | YES | REVB | REVC | close | Remove 20dB coupler which was used for testing 2G module-(2G module is moved to Rf board)
29 |  | U4101 | Removed LDO 2P5V in the design | Yes | YES | YES | REVB | REVC | close | Used resistor divider circuit from 3P3V to 2P5V -low current consumption(pullups)
30 |  | CON2,CON1,CON4 and CON3 | Added SMP connector | Yes | YES | YES | REVB | REVC | close | Added RF connectors for TX and RX path of front end-19S101-40ML5
31 |  | MH5,MH7,MH1,MH3,MH6,MH8,MH2,MH4 | Mounting holes added | - | - | - | - | - |  | Mounting holes added for RF board
32 |  | ATT2400,ATT2401,ATT2300,ATT2301,ATT2602,ATT2603,ATT2600,ATT2601,ATT3001,ATT3000,ATT2901,ATT2900,ATT3202,ATT3203,ATT3200,ATT3201 | Removed fixed attenuators from the design | Yes | YES | YES | REVB | REVC | close | Removed attenuators and provided resistors pad provision
33 |  | J10,U7161,U7162 | Rf connectors and 3 pin header added | Yes | YES | YES | REVB | REVC | close | connetor and jumper provision for 10MHz clock and fram sync signal
34 |  | U40,U41 | 3P3V_TIVA powersupply given to temparature sunsors | - | YES | YES | REVB | REVC | close | 3P3V_TIVA always all power supply given to TEMP sensor for monitoring board temparature
35 |  | U1905,U2003,U1803 | Removed temp sensor alert to watchdog comparator | - | YES | YES | REVB | REVC | close | Individual alerts for temparature and watchog comparator alert
36 |  | L2201,L2801 | changed to 18nH | YES | YES | NO | REVB | REVC | close | MGA-30216 matching on both chains
37 |  | L2205,L2805 | unmounted | YES | YES | NO | REVB | REVC | close | MGA-30216 matching on both chains
38 |  | C2210,C2810 | changed to 3.3pF | YES | YES | NO | REVB | REVC | close | MGA-30216 matching on both chains
39 |  | C2214,C2815 | changed to 1pF | YES | YES | NO | REVB | REVC | close | MGA-30216 matching on both chains
40 |  | C2213,C2813 | unmounted | YES | YES | NO | REVB | REVC | close | MGA-30216 matching on both chains
41 |  | L2203,L2803 | unmounted | YES | YES | NO | REVB | REVC | close | MGA-30216 matching on both chains
42 |  | C2206,C2806 | changed to 10pF | YES | YES | NO | REVB | REVC | close | MGA-30216 matching on both chains
43 |  | C2207,C2807 | changed to 10pF | YES | YES | NO | REVB | REVC | close | MGA-30216 matching on both chains
44 |  | L2212,L2812 | changed to 9.1nH | YES | YES | NO | REVB | REVC | close | MGA-30116 matching on both chains
45 |  | C2230,C2830 | changed to 10pF | YES | YES | NO | REVB | REVC | close | MGA-30116 matching on both chains
46 |  | C2233,C2833 | changed to 2.7 pF | YES | YES | NO | REVB | REVC | close | MGA-30116 matching on both chains
47 |  | C2234,C2834 | unmounted | YES | YES | NO | REVB | REVC | close | MGA-30116 matching on both chains
48 |  | C2228,C2828 | changed to 100 pF | YES | YES | NO | REVB | REVC | close | MGA-30116 matching on both chains
49 |  | L2213,L2813 | unmounted | YES | YES | NO | REVB | REVC | close | MGA-30116 matching on both chains
50 |  | C2410,C3010,C3030,C2439 | changed to 100 pF | YES | YES | NO | REVB | REVC | close | Low band optimization to achieve maximum power
51 |  | C2411,C4470,C4471,C4472 | changed to 12 pF | YES | YES | NO | REVB | REVC | close | Low band optimization to achieve maximum power