## feedback
Design Feedback
FB_CONNECT1_SYNC_LIFE-3_V0P10
Sno. | Page #/Section | Schematic/Layout | Feedback | Comments | Status (Open/Close)
1 | 3 | Schematic | LTE_RESET, add buffer to the RESET (check with Shreesha for buffer location) | Added buffer | Close
2 | 3 | Schematic | Add 3 pole RC filter on 40Mz reference output, NET "R_LTE_REF_OUT_10MHz" | Added filter provision | Close
3 | 3 | Schematic | change NETNAME from "R_LTE_REF_OUT_10MHz" to "R_LTE_REF_OUT_40MHz" | Updated | Close
4 | 3 | Schematic | change R16, R17, R18 according to 40MHz output; R16=Mount, R17=Mount, R18=No-mount | Updated | Close
5 | 10 | Schematic | Disconnect R_LTE_TXD_CPU from J4 pin 50 | Updated | Close
6 | 3, 4, 10 | Schematic | Add SPDT switch to multiplex signals "R_LTE_TXD_CPU" and "R_LTE_TXD_GPS". Switch output to connect to J4 pin 20. Multiplxer control to be connected to the unused pin of I/O expander U28 | Added Switch | Close
|  |  | Any one of R10940 & R10941 should be no mount. In the current condition, 2 outputs are shorted which will damage the module. Any one of the resistor should be no mount | R10940 made DNP | Close
|  |  | R20 should be no mount | Updated | Close
One of R36 or R3 should be no mount
|  |  | There is a enable connection from IO expander to U6. It depends whether you want to power on the board by default or you want the board to be powered OFF by default. If you want the 5V to be off during power up, and TIVA will enable this, then R83 should be no mount. In this case, it is OK. Otherwise, This may not be right because, the IO expander is working at 3.3V and the pull up on the EN pin is to 12V. During power up, this will have adverse effects of 2 different power domains getting a path to one another even though there is a current limiting resistor. In order to acheive this, you will have to use a MOSFET to power OFF the 8640. | R83 made DNP | Close
|  |  | Better to add a 100K pull up on pin 8 of U2 | Added | Close
|  |  | Make R24 mount as it is open drain pin | Updated | Close
| 2 | Schematic | Block diagram is confusing. - What is SP2T in LTE-lite path switcing in/out: - - indicate that "RF_IN_SPDT" is coming from GPS+Ir antenna connected to SDR). - - indicate that there is an RF jumper coax from U.FL to Ir module - Which direction is the MM8430-2610RB3 looking when the switch connector gets enabled? Why is a probing test point should in a block diagram (as it's presence in this block diagram appears to give it more significance than just a test point). - Where is the path the teh LTE-lite module that bypasses the LNA and filters? (or has this been excluded?)