## Sheet1
Layer 1
1 | Extend the Plane shape upto test points, check for all the supply
2 | Route the trace in the outer edge and add gnd vias,route as per below image
3 | Load the 3D model for the samtec connector and check the vias inside the connector.
4 | Clean the trace bends
5 | Add gnd stiching vias
6 | Remove single point copper
7 | Check the trace width
8 | change the trace width
9 | Adjust the vias to increase the plane flow
10 | Move the vias and connect the gnd shape
11 | Move the via from the mention location
12 | Move the via and connect the gnd plane shape
13 | Change the date and life no
Layer 3
14 | Move the traces in layer 3 and fill the gnd shapes, othewise layer1 RF trace split with these traces
Layer 5 | Remove the 3.3VD_TIVA plane under the RF section, Rf section don’t have the Gnd plane.In layer 4 cut the plane shape, it will take less current , route the supply voltage with 20 mil trace width
Layer 6 | Remove the 12 v plane in layer 6
ESD symbol add inside the board
silkscreen allignment to be done
Board dimension to be change
Assembly drawing to be changed