## Revision History
Project | Open Cellular Connect -1
Board Name | Software Defined Radio
Build | Life - 3 (Rev C)
Changes Log | From RF_SDR Life - 2 to SDR_Life-3
Change History
Date | Version | Author | Remarks
30th NOV 2016 | Release Version for SDR Life-3

## Change_log
SDR Life-3 Design Change Log
S.No | Date | Reference Designator | Changes Done | Impact to BOM | Impact to Schematic | Impact to Layout | Impacted Design Revision | Fixed Design Revision | Fix Status | Reason for change
1 | 2016-11-30 | C192, U13 C7 | Connected net from C192 to C7 pin of U13 | No | Yes | Yes | Rev B | Rev C |  | 19.2MHz crystal out to FX3 IC net missing due to manual error in schematics
2 |  | SW11 | instead of JP1 connector used slide switch | yes | Yes | Yes | Rev B | Rev C |  | slide switch provosion for select pin
3 |  | SW10 | instead of J3301 connector used slide switch | yes | Yes | Yes | Rev B | Rev C |  | slide switch provosion for 5VD (VBUS pin of FX3)
4 |  | SW12 | instead of JP2 connector used slide switch | yes | Yes | Yes | Rev B | Rev C |  | slide switch provosion for select pin
5 |  | U7145 | I/O expander added for strap pins | yes | Yes | Yes | Rev B | Rev C |  | strap pin implementation
6 |  | C2032,C4612,C4613,C4614,D1239,D1240,D3001,FB11,FB12,Q132,R1230,R1231,R1232,R1233,R1234,R1235,R1240,R1242,R1243,R1244,R1246,R1247,R1248,R1450,R1451,U252,U293 | power switch added | Yes | Yes | Yes | Rev B | Rev C |  | power switch implementation
7 |  | C693,C694,C695,C696,FB6318,R11080,R11092,U7132 | LDO is added for VCC_MGTAVTT | Yes | Yes | Yes | Rev B | Rev C |  | LDO is added for VCC_MGTAVTT (for PCIe connection)
8 |  | C690,C691,C692,R11075,R11076,R11077,R11078,R11079,U7131 | reset ciruit for VCCMGTAVTT_OK | Yes | Yes | Yes | Rev B | Rev C |  | reset ciruit for VCCMGTAVTT_OK
9 |  | MH10-MH12 | Mounting holes added | No | Yes | Yes | Rev B | Rev C |  | Mounting holes added
10 |  | U7146 | ESD protection circuit symbol and ref des change from U34 to U7146 | Yes | Yes | Yes | Rev B | Rev C |  | ESD protection circuit symbol
11 |  | U235,U7143 | 6 GPIO is connected to FPGA through level translator from High speed connectorJ4. | Yes | Yes | Yes | Rev B | Rev C |  | GPIO connections added
12 |  | U7147,U220 | Reset implementation for AD9361 changes | Yes | Yes | Yes | Rev B | Rev C |  | Reset implementation for AD9361
13 |  | U7144 | Temp Sensor added | Yes | Yes | Yes | Rev B | Rev C |  | Temp Sensor added
14 |  | R550,R551,R552,R553 | USB 3 related changes have implemented-replace extra caps with 0 ohm resistors | Yes | Yes | No | Rev B | Rev C |  | replace 0.1uf capacitor to 0ohm resistor
15 |  | U7130 | EPROM added for FPGA | Yes | Yes | Yes | Rev B | Rev C |  | EPROM added for FPGA
16 |  | U7129 | 1:6 MUX added for SPI between EEPROM and FPGA | Yes | Yes | Yes | Rev B | Rev C |  | 1:6 MUX added for SPI between EEPROM and FPGA
17 |  | U411,U7148,U7149,U7150 | PCA9517A(Level-Translating I2C-Bus Repeater) added for I2C2,I2C4,I2C3 | Yes | Yes | Yes | Rev B | Rev C |  | PCA9517A(Level-Translating I2C-Bus Repeater) added for I2C2,I2C4,I2C3
18 |  | J3305 | Sync Board Connector | Yes | Yes | Yes | Rev B | Rev C |  | Sync Board Connector
19 |  | J3304 | RF Board Connector added | Yes | Yes | Yes | Rev B | Rev C |  | RF Board Connector added
20 |  | U7134 | added level translator for VCCMGT_VCCO18_VCC33 signal | Yes | Yes | Yes | Rev B | Rev C |  | added level translator for VCCMGT_VCCO18_VCC33 signal
21 |  | U1800 | PCA9557 io expander added for TIVA IO's control | Yes | Yes | Yes | Rev B | Rev C |  | PCA9557 io expander added for TIVA IO's control
22 |  | TP24-TP40,TP90,TP91,TP92 | Test points added for AD9361 signals | No | Yes | Yes | Rev B | Rev C |  | Test points added for AD9361 signals
23 |  | U7141 | Clock buffer and divider added | Yes | Yes | Yes | Rev B | Rev C |  | Clock buffer and divider added
24 |  | U9,U7131,U7132,J4 | PCIE interface implemented to FPGA | yes | Yes | Yes | Rev B | Rev C |  | PCIE interface implemented
25 |  | R11229-R11240 | added 0 ohms for CTRL_IN and CTRL_OUT signals | Yes | Yes | Yes | Rev B | Rev C |  | added 0 ohms for CTRL_IN and CTRL_OUT signals
26 |  |  | Test points for power and clock ,lock detect,SPI lines | Yes | Yes | Yes | Rev B | Rev C |  | Test points for power and clock ,lock detect,SPI lines
27 |  | Y3 | Part number change | Yes | Yes | No | Rev B | Rev C |  | Part number change
28 |  | SW1 | SW1 switch added . | Yes | Yes | Yes | Rev B | Rev C |  | SW1 switch added .
29 |  | U7151,U7152,U7153 | level translator added | Yes | Yes | Yes | Rev B | Rev C |  | level translator added
30 |  | U9 | FPGA part number changed | Yes | Yes | No | Rev B | Rev C |  | FPGA part number changed
31 |  | U7139 | provision for AD9361 external TX/RX LO Connector | yes | Yes | Yes | Rev B | Rev C |  | provision for AD9361 external TX/RX LO Connector
32 |  | R11073 | This resistor value change to 620 | yes | Yes | No | Rev B | Rev C |  | This resistor value change to 620
33 |  | R690,R691 | resistor value changed to 300ohms for 5VD_B | yes | Yes | No | Rev B | Rev C |  | resistor value changed to 300ohms for 5VD_B
34 |  | R193,R194,R195,R196 | resistor property changed to DNP | yes | Yes | No | Rev B | Rev C |  | resistor need to be DNP
35 |  | D10153 Diode,R1880 added . | Connected to J4.J9 | yes | Yes | Yes | Rev B | Rev C |  | Connected to J4.J9
36 |  | A9,A10 spacer M3 added | spacer added | yes | Yes | Yes | Rev B | Rev C |  | spacer added
37 |  | Added R720,C720,C4665,C4664. | for clock circuit | yes | Yes | Yes | Rev B | Rev C |  | for clock circuit
38 |  | C4663 | for PLL | yes | Yes | Yes | Rev B | Rev C |  | for PLL
39 |  | J3304-B13,B14,F8,F12-GND added. | RF connector | No | Yes | Yes | Rev B | Rev C |  | RF connector
40 |  | U7154 | AND gate added to control power for RF | yes | Yes | Yes | Rev B | Rev C |  | AND gate added to control power for RF
41 |  | C4667 | added C4667 for SIN_CLK_BUFF_OUT3 (clock for FPGA) | yes | Yes | Yes | Rev B | Rev C |  | added C4667 for SIN_CLK_BUFF_OUT3 (clock for FPGA)
42 |  |  | Capacitor change to X5R to X7R | yes | Yes | No | Rev B | Rev C |  | Capacitor change to X5R to X7R
43 |  | R690,R691,FB11,FB12 | Derating failure-change part number | yes | Yes | No | Rev B | Rev C |  | Derating failure-change part number
44 |  | U9.N10 and U9,N9 | FPGA unused pins connected to GND | No | Yes | Yes | Rev B | Rev C |  | FPGA unused pin termination
45 |  | R10906 | R10906 resistor changed to 56E | yes | Yes | No | Rev B | Rev C |  | resitor value change
46 |  | R11337 | R11337 resistor changed to 91E | yes | Yes | No | Rev B | Rev C |  | resistor value change
47 |  | R10896, R1580 | R10896 made as mount and R1580 made as DNP | yes | Yes | No | Rev B | Rev C |  | resistor value change